## Slide 1: Silver Line – Update
Status
Phase 1
  Punchlist – Ongoing
    VDOT, WMATA, and Fairfax County
    Fairfax County 274 items, 81 closed
    Project Closeout continues until the end of 2015
    Task Order Contract to complete remaining punch list items
  Contingency Remaining - $8.8M
    Not all claims finalized – Forecasted to be completed on budget ($2.905B)
  Wiehle Garage – 85% parking utilization
  Ongoing work
    Old Meadow Road
    Art in Transit
Phase 2
  Design Build Status
    Overall Project – 18%
    Design – 81%
    Construction – 11%
  Highlights
    Enabling work on Herndon and Innovation Center Station 1st and 2nd quarter 2015
    Aerial Guideway at Dulles Airport under construction
    Rail Yard at Dulles Airport in design
Budget - $2.775B
  Total Contingency - $551.M (Remaining $533.5M)
County Activities
Phase 2 Design Reviews
County Coordination
  Town of Herndon
  Adjacent Land Owners
  Project Partners (MWAA, VDOT, DRPT, WMATA, Loudoun County)
  Fairfax Connector
Phase 1 Close Out and Punchlist
SE and 2232 for Pavilion and TPSS 13 at Herndon submitted to Fairfax County
Community meetings held on Herndon Station (south side) garage
Phase 1 and Phase 2 Annual Dulles Rail Tax Advisory meeting held in March 2015
March 17, 2015

## Slide 2: Silver Line – Update
County Activities
  Herndon & Innovation Center Station garages - DPWES lead for design/construction
  Innovation Center Station Garage ($57M)
    Rezoning was approved July 2014
    Gordon and HGA Architects have been selected as part of the project team
    Schematic design complete
    Progressing with value engineering at the end of March 2015
    Start of construction expected March 2016
    Continued coordination with Rocks and MWAA
    Completion April 2018
  Herndon Garage ($58.7M)
    2232 application was approved June 2014
    Gordon and HGA Architects have been selected as part of the project team
    Schematic design complete
    Value engineering is scheduled for April 2015
    Start of construction expected April 2016
    Public presentation to the community March 9, 2015
    Ongoing coordination with MWAA over scope of work on-site and construction activities
    Completion April 2018
TIFIA
  Fairfax County Closed a $ 403.3M TIFIA Loan in December 2014
March 17, 2015