## Slide 1: Transportation Priorities Plan Future Updates
Ray Johnson and Tom Biesiadny
Fairfax County Department of Transportation
Board Transportation Committee
December 1, 2015

## Slide 2: Background
On January 28, 2014, the Board of Supervisors adopted the six-year transportation project priorities for FY 2015-FY 2020. The Transportation Priorities Plan (TPP) included approximately 220 projects worth about $1.4 billion from multiple local, regional and state funding sources.
The Board also directed staff to return with project timelines that consider the following:
  Advance highest priority projects first.
  Spread projects across six-year timeframe.
  Respect funding limitations, restrictions, and availability; and follow guidelines or requirements set by funding decision-makers (NVTA, CTB, etc.).
  Consider project complexity, size, and geographic location.
  Consider input from implementation partners, particularly VDOT.

## Slide 3: What Was Approved
Projects | $ in mils
Interchanges | $195.0
Extensions | $115.3
Spot Roadway/Intersection Improvements | $66.0
Roadway Widenings | $381.3
Transit Capital/Operating | $326.8
Pedestrian and Bicycle Projects | $204.0
Capital Reserve | $10.0
Additional Funding for Previously Approved Projects | $132.7
Total | $1,431.1

## Slide 4
Seven projects have been completed
Pedestrian signalization improvements completed by VDOT:
Braddock Rd/Olley Ln
Backlick Rd/Edsall Rd
Edsall Rd/Montgomery St
Route 50/Gallows Rd
Jermantown Rd/Arrowhead Dr
Route 236/Old Columbia Pike
Franconia Rd/Telegraph Rd
Status of TPP Project Implementation
*Does not include projects approved prior to January 28, 2014.
Notes: 1. Does this include projects under construction by VDOT, like the signal rebuild projects AND projects like the Little Rocky Run Bridge Replacement project.

## Slide 5
Under Construction
Town Center Parkway Underpinning (as part of Dulles Rail)
Route 7 DTR Bridge Widening
Design Underway
Frontier Drive Extension w/ braided ramps
Rolling Road Widening Old Keene Mill to Fairfax County Parkway
Route 1 from Mt Vernon to Napper
Route 7 from Jarrett Valley Drive to Reston Ave
Status of TPP Project Implementation (cont)
*Does not include projects approved prior to January 28, 2014.
Notes: 1. Does this include projects under construction by VDOT, like the signal rebuild projects AND projects like the Little Rocky Run Bridge Replacement project.

## Slide 6
Studies/Preliminary Engineering Underway
I-66/Route 28 Interchange
Fairfax County Parkway/Popes Head Road Interchange
Seven Corners Interchange Improvements
Soapstone Drive Overpass
Shirley Gate Road
Fairfax County Parkway (I-95 to Route 1)
Braddock Road Widening
Route 1 from Armistead to the Occoquan
Route 28 from PWC to Route 29
Dulles Toll Road Connector Ramp
Route 7/Route 123 Interchange Rebuild
Lorton Arts Access Road
Jefferson Manor Phase IIIB
Roadway Spot/Intersection Improvements (8)
Pedestrian Improvements (46)
Richmond Highway Public Transportation Initiative
  Bus stop projects (17)
Richmond Highway Bus Rapid Transit
Innovation Center Metrorail Station
Herndon Bus Garage Renovations
Bicycle improvements projects (2)
Status of TPP Project Implementation (cont)
Notes: 1. Does this include projects under construction by VDOT, like the signal rebuild projects AND projects like the Little Rocky Run Bridge Replacement project.

## Slide 7: Updating the TPP
Staff has discussed updating and revising the Board’s TPP on a recurring basis.
What needs to be done?
  Update project costs and timelines.
  Revise revenue estimates, including adding revenue from additional years.
  Identify additional projects for consideration.
  Perform Benefit/Cost Analysis on new projects.
  Conduct outreach.
How much time will it take?
  Each step requires considerable time and effort.
  Staff proposes updating the TPP once every three years.
    Allows time for progress on project implementation.

## Slide 8: Proposed Schedule of Activities
Summer 2015 - Winter 2016
First discussion with Board concerning the TPP update.
Update project costs.
Revise revenue estimates, including additional years.
Update project timelines and cash flows.
Identify the amount of estimated funding available for new projects.
Identify new projects for consideration, including projects from Board, public, business community, and others.
Spring 2016
Begin outreach planning/production.
Prepare BCAs for new projects.
Summer 2016
One-on-One meetings with Board members.

## Slide 9: Proposed Schedule of Activities
Late Fall 2016
Community outreach/meetings.
Prepare BCAs for new projects resulting from community input.
Also rank projects on non-BCA measures.
Revised estimated costs for all new projects
Spring 2017
One-on-One with Board members.
Return to Board Transportation Committee.
Summer - Fall 2017 (FY18)
Board approval of TPP update (FY19-24)

## Slide 10: Factors Potentially Impacting TPP Update
Revenue
Projections for state revenue unknown due to HB2.
  However, staff will assume a reasonable level of support that should be available to the County.
Other revenue sources appear to be generally tracking with projections.
Revised Cost Estimates
Increased cost estimates will be addressed with:
  Cost reductions from other projects
  Increase revenues above estimates, if any (FY15 – FY20)
  New projected funding (FY21 – FY24)

## Slide 11: NVTA Process and the TPP Update
NVTA has begun updating TransAction, its long-range transportation plan. TransAction includes transportation network and land use information through the current Regional Constrained Long Range Plan (CLRP) outlook, currently 2040.
  The plan is expected to be complete in fall 2017.
Projects must be included in TransAction to be eligible for NVTA regional funding.
  NVTA’s next funding Call for Projects will likely occur after the TransAction update is complete.
County staff is reviewing the current TransAction plan, participating in the update, and will return to the Board to discuss recommended project changes and additions.
The County will submit projects to NVTA for inclusion in the Plan.

## Slide 12: HB2 Process and the TPP Update
HB2 applications for FY18 – FY23 due Fall 2016.
  Only unprogrammed revenues (FY22 – FY23) will be considered for approval.
  Will include revenues for FY18 – FY21, but these revenues were programmed under previous SYIP approval (~June 2016).
  Then, applications will be submitted every other year.
Next round of HB2 applications (FY20 – FY25) will be due Fall 2018.

## Slide 13: Next Steps
Receive feedback from the Board on staff’s proposed schedule and process for the TPP update.
Begin working on the scheduled activities and follow up on suggestions from the Board.
Provide periodic progress reports to the Board.
Long term impacts on the TPP of the I-66 Outside the Beltway project to be determined based on CTB action.
Staff will return to the Board in February 2016 with funding allocation adjustments based on changes since January 28, 2014.

## Slide 14: Questions/Comments?