## Slide 1: Update of Transportation Priorities Plan
Transportation Advisory Committee
June 20, 2017
Tom Biesiadny/Ray Johnson
Fairfax County Department of Transportation

## Slide 2: Background
2012 - Countywide Dialogue on Transportation (CDOT)
  Transportation needs, potential revenue sources
2013 – General Assembly approved state and regional transportation funding (HB 2313)
Countywide Dialogue continued; focused on projects and project selection
All available revenues considered for Transportation Priorities Plan (TPP)
January 2014 - TPP approved by the Board
May 2014 – Project timelines completed

## Slide 3: TPP (FY 2015 to FY 2020)
Funding Level: $1.4 B over Six Years
Included approximately 220 projects
Include reserves for several project areas
  Fairfax County Parkway
  Transit (Including Metro, Richmond Hwy,
  Route 7 and others)
  Bicycle and Pedestrian
  Roadway Spot Improvements
Reminder: Several large projects
were only partial funded in TPP

## Slide 4: Progress Since January 2014
  Projects
  72 projects in queue/32 projects currently in scoping
  95 projects in design
  13 projects in land acquisition/utility relocation/pre-construction
  22 projects completed
  10 projects under construction
  8 studies completed/18 underway
    Cleveland Ramp
    Route 7/123 Interchange
    Route 123 Superstreets
Does not include projects previously approved as part of the Board’s 1st – 3rd Four Year Plans.

## Slide 5: Changes Since January 2014
  I-66 Inside and Outside the Beltway
  Several projects included in the reserves have been further defined
    Transit
      Richmond Highway transit solution: Bus Rapid Transit (BRT)
      Metro: continuing discussions regionally
      Route 7 transit solution: BRT
    Fairfax County Parkway (FCP): First Priority: Route 29 to Route 123
      Additional study of the entire FCP underway
    Many bicycle, pedestrian, and Spot Roadway Improvements

## Slide 6: Comp Plan Amendments Since January 2014
    Reston (February 2014)
      Reston Transportation Funding Plan Adopted – April 2017
      Project Prioritization Completed
    Seven Corners (July 2015)
      Next steps, Project Prioritization
      and Funding
    Richmond Highway underway

## Slide 7: TPP Update (FY 2018 to FY 2023)
Financial Analysis
  Incorporating all revenue sources:
    State: Smart Scale, Revenue Sharing
    Federal: New Starts, Congestion Mitigation Air Quality, Regional Surface Transportation Program, and Transportation Alternatives Grants
    Local: C&I, NVTA 30%, General Obligation and Revenue Bonds, Service Districts
    Regional: NVTA 70%
    Private: Proffers, In-kind contributions
Includes:
  Tysons Transportation Funding Plan
  Reston Transportation Funding Plan

## Slide 8: Process
  Started in calendar year 2016
  Update cost estimates and timelines for current projects
  Unfunded project input received from a variety of sources (citizens, board, schools, etc)
  Perform Benefit Cost Analysis (BCA) on new projects
  Remove completed and cancelled projects
  Over $600M in new revenues (FY 2021 to 2023) needed to ensure:
    All projects that were intended to be fully funded between FY 2015 and 2020 are fully funded due to increased costs, scope changes, inflation, unexpected situations, citizen input, etc.
    Projects partially funded between FY 2015 & 2020 receive the remainder of funding.
  Funding level available for new projects in TPP Update: $170M

## Slide 9: Process Continued
  Does not include additional funding Fairfax County may receive from the $500M concession payment associated with the I-66 Express Lanes project (Outside the Beltway)
  Also does not include investments associated with the Atlantic Gateway project, or projects and services that can be funded with toll and transit funding associated with the I-66 Outside the Beltway, I-66 Inside the Beltway, and I-395 Express Lanes projects.

## Slide 10: Recap of Criteria for Project Selection (Not in Priority Order)
Congestion Reduction*
Economically Disadvantaged Populations
Mode Balance
Safety
Travel Time Savings*
Community Input
School and Park Access
Regional Consideration (included in NVTA TransAction 2040)
Countywide Balance
Disabled/Elderly Populations
Economic Development (support for revitalization areas and major Activity Centers)
Healthy Communities Initiative
Air Quality*
*Included in the Cost Benefit Analysis

## Slide 11: Reserve Funding (Input Requested)
  Funding level available for new projects in TPP Update: $170M.
  Recommend using $100M for new projects, and $70M for projects in need of additional funding.
  Considerations in allocating new funds:
    Future funding plans (Innovation, Seven Corners, Richmond Hwy, etc)
    Metro/Transit
    Atlantic Gateway
    Fairfax County Parkway
    Unexpected cost overruns
    Small scale projects that may arise between FY 2021 and FY 2023

## Slide 12: Potential Projects
  List of potential projects consolidated from various sources
  Cost estimates developed
  Benefit Cost Analysis (BCA) being conducted
  Bicycle and Pedestrian BCA being prepared with separate methodology
  Non-BCA Factors being evaluated
  Efforts included outreach to multiple County agencies, the public, and various associations.
  Review of project list by district (attachment)

## Slide 13: Public Outreach (Input Requested)
  Meeting with TAC on June 20 to receive input on outreach efforts
  Proposed outreach strategy to include:
    Direct-to-community outreach including community meetings (September-October 2017)
    Partner agency outreach
    Online survey and geo-targeted social
    media advertising
    Traditional media outreach
    and advertising

## Slide 14: Schedule (Tentative: Input Requested)
  July 18: Board Transportation Committee Meeting
    Finalize potential project list and outreach activities
  August: Preparation for public outreach; preparation of materials, etc.
  September-October: Public Outreach
  October-November: Staff review of input and preparation of draft recommendations
  Mid-November/Early December: One-on-One meetings with Supervisors
  December 12: Board Transportation Committee Meeting
    Review of Final Draft Plan Recommendations
  January-February 2018: Board Adoption

## Slide 15: Questions?